## Read first
Purpose | Track evidence for an actual launch. This file does not connect to Shopify, run tests or certify readiness.
How to use | Assign named owners and due dates. Mark Pass only with observed evidence. Mark Not applicable with a reason. Keep Failed and Blocked items visible until reviewed.
Scope | Record the store, theme, account type, tier, channels, payment setup and test date. A test in one environment does not establish behavior in another.
Protect customers | Use test customers and supported payment testing. Keep test messages away from real customers. Avoid putting personal data, passwords or access tokens into this shared workbook.
Exceptions | Refund, cancellation and reward reversal behavior must be observed and reconciled with the published policy. Acceptance criteria are not promises of automatic app behavior.
Launch decision | The Launch decision sheet is a human approval record. There is no automated readiness score. Correct charges and usable promised benefits are required before expanding the affected path.
Guide | https://www.memberply.com/guides/shopify-loyalty-program-implementation

## Rollout tasks
Stage | Task | Suggested role | Required evidence | Named owner | Due date | Status | Evidence / notes
Scope | Approve the audience, reward rules, budget and success criteria. | Program owner | Signed offer brief and business case |  |  | Not started
Dependencies | Confirm account type, channels, payment flow, integrations and data ownership. | Store administrator | Recorded configuration and named dependency owners |  |  | Not started
Configuration | Set tiers and benefits, connect account access and prepare customer-facing copy. | Store administrator + marketer | Saved settings and matching offer copy |  |  | Not started
Testing | Complete applicable test cases and investigate every failure. | QA owner + support lead | Evidence, actual outcomes and resolved blockers |  |  | Not started
Pilot | Invite a limited eligible audience and monitor the promised experience. | Program owner + support lead | Support coverage, daily issue review and pilot decision date |  |  | Not started
Rollout | Expand only after reviewing customer experience and contribution. | Business owner | Explicit launch decision and next review date |  |  | Not started

## Test cases
ID | Area | Test action | Pass evidence | Applies to | Owner | Due date | Status | Actual result / evidence | Issue / next action
T01 | Joining | A new eligible customer joins the intended tier. | Membership status, tier, price and billing interval match the offer. | Any paid or free tier |  |  | Not started
T02 | Recurring checkout | Add the membership from each advertised purchase path, including quick add if used. | The selected selling plan, price and interval reach checkout; a recurring plan is not silently sold as a one-time product. | Recurring paid tier |  |  | Not started
T03 | Account access | Sign in as an active member; repeat as a nonmember and an ended member. | The promised benefits are discoverable and access matches each customer’s actual eligibility. | All programs |  |  | Not started
T04 | Eligible earning | Place an eligible order using the configured reward basis. | Reward amount matches the documented rate, exclusions, cap, tax and shipping settings. | Purchase rewards |  |  | Not started
T05 | Ineligible earning | Place an excluded-product order or one below the earning threshold. | No reward is earned where the published rules exclude it. | Conditional rewards |  |  | Not started
T06 | Credit delivery | Earn credit, then follow the supported account sign-in and delivery flow. | The earned reward and issued balance can be reconciled; no duplicate value appears. | Credit rewards |  |  | Not started
T07 | Redemption | Use an available reward on an eligible order larger than its value. | Correct value is applied once, the remainder is payable and the balance updates. | Redeemable rewards |  |  | Not started
T08 | Discount combinations | Try the member benefit with an ordinary promotion and an excluded item. | The actual combination and exclusions match the published offer. | Discount benefits |  |  | Not started
T09 | Partial refund | Refund part of an order that earned a reward; inspect the reward and balance afterwards. | Actual adjustments are recorded and reconciled with the written policy, with a manual procedure if needed. Do not assume automatic reversal. | Purchase rewards |  |  | Not started
T10 | Full refund after redemption | Test a refunded earning order after its reward has been spent. | Support can explain and resolve the resulting balance under the approved policy without issuing duplicate value. | Purchase rewards |  |  | Not started
T11 | Cancellation and expiry | End or cancel a test membership and check at the configured access-end time. | Billing status, benefit access and previously issued rewards follow the stated rules; cancellation is not assumed to erase existing credit. | Paid or expiring membership |  |  | Not started
T12 | Renewal and failed payment | Exercise the configured renewal and failed-payment paths in a supported test setup. | Charges, notifications and access timing match the configuration; staff know how to investigate a failure. | Recurring paid tier |  |  | Not started
T13 | POS customer selection | Attach the correct customer to a POS cart and open the Memberply tile. | Staff see the correct member and available benefits; test redemption separately from benefit display. | In-store program |  |  | Not started
T14 | POS purchase and order tracking | Complete an eligible in-store test purchase and inspect membership or reward status. | The intended membership or reward outcome is recorded, including any pending-payment interval. | In-store program |  |  | Not started
T15 | Notifications | Review each enabled joining, benefit, renewal and cancellation message. | Recipient, amount, timing, link and wording match the actual event; duplicate messages are removed. | Enabled messages |  |  | Not started
T16 | Measurement | Walk through an invitation, join, earning event and redemption in the reporting plan. | Sources distinguish visits, joins, rewards, redemption and purchases; exclude test activity where possible. | All programs |  |  | Not started

## Launch decision
Decision item | Prompt | Your record
Store and launch scope | Record account type, tier, channels, theme and relevant configuration.
Critical failures | List unresolved wrong-charge, access, duplicate reward or policy mismatch issues.
Accepted limitations | Name the decision owner, rationale and planned resolution for each noncritical issue.
Support readiness | Record support owner, coverage and investigation procedure.
Pilot and measurement | Record audience, baseline, observation window and success/stop criteria.
Incident response | How to stop new promotion while protecting existing members and issued value.
Decision | Go / No-go / Limited pilot, with rationale and evidence.
Approver and date | Record the accountable approver and decision date.
Next review | Record when and by whom the pilot will be reviewed.