## Read first
Purpose | Editable project brief, not an integration, quote or guarantee of Memberply feature availability.
Use | Fill the blue response, owner and evidence columns. Confirm each requirement with documentation and observed tests. Duplicate mapping rows as needed.
Status | Confirmed means you have evidence for this row. The workbook does not calculate readiness or approve a launch.
Example | The Worked example sheet is a fictional one-way CRM project. Receiver logic and destination mapping require implementation and testing.
Share safely | Use test identifiers and configuration references. Do not enter API keys, signing secrets or customer exports.
CSV | The CSV includes every brief and example row in one table. It has no tabs, dropdowns or styling.
Guide | https://www.memberply.com/guides/shopify-loyalty-program-integrations#integration-brief
Source | https://help.memberply.com/integrations/webhooks

## Project scope
Section | ID | Decision / test | Guidance | Your response / actual result | Named owner | Evidence / reference | Status
Project scope | S01 | Business outcome | Name one member journey and the destination action it should enable. |  |  |  | Not reviewed
Project scope | S02 | Systems and direction | List source store, destination and one-way or two-way direction. Confirm supported APIs before promising writes. |  |  |  | Not reviewed
Project scope | S03 | Connection choice | Native integration, outbound webhook receiver or separately scoped custom work? Record the gap that requires development. |  |  |  | Not reviewed
Project scope | S04 | Events and timing | List exact supported events and a target delay to agree. A target is not a Memberply SLA. |  |  |  | Not reviewed
Project scope | S05 | Existing members | Agree a supported initial load, reconciliation, cutoff and owner. Future events alone are not a backfill. |  |  |  | Not reviewed
Project scope | S06 | Volume and capacity | Record expected activity and peaks, destination limits and how capacity will be tested. |  |  |  | Not reviewed
Project scope | S07 | Boundaries | List excluded workflows: for example reward balances, billing migration, marketing consent or cross-store sharing. |  |  |  | Not reviewed
Project scope | S08 | Delivery and ownership | Name build, test, launch and maintenance owners; agree deliverables, quote and support separately. |  |  |  | Not reviewed

## Field mapping
Section | ID | Decision / test | Guidance | Your response / actual result | Named owner | Evidence / reference | Status
Field mapping | F01 | Source identity | Record shop domain plus Shopify customer ID; map to the destination record. Do not match across stores by email alone. |  |  |  | Not reviewed
Field mapping | F02 | Membership status | Record verified source field, destination field, meaning, transformation, null behavior and authoritative system. |  |  |  | Not reviewed
Field mapping | F03 | Tier identifier and label | Keep stable tier identity separate from display name; define clearing behavior when inactive. |  |  |  | Not reviewed
Field mapping | F04 | Event identity and time | Record event ID and occurred-at timestamp paths; define deduplication and late-event policy. |  |  |  | Not reviewed
Field mapping | F05 | Membership dates | List only dates actually needed; verify scheduled cancellation coverage separately from immediate cancellation. |  |  |  | Not reviewed
Field mapping | F06 | Additional field | Record source path, availability, destination, transformation, null handling and owner. Duplicate this row as needed. |  |  |  | Not reviewed
Field mapping | F07 | Consent boundary | Membership status is not marketing opt-in. Preserve destination consent and verify any messaging filters. |  |  |  | Not reviewed

## Operations
Section | ID | Decision / test | Guidance | Your response / actual result | Named owner | Evidence / reference | Status
Operations | O01 | Verification and permissions | Name the receiver verification method and credential owner. Do not put secrets in this workbook. |  |  |  | Not reviewed
Operations | O02 | Durable receipt | Agree how the receiver persists or queues an accepted event before acknowledging it. |  |  |  | Not reviewed
Operations | O03 | Duplicate processing | Define an idempotency key and replay behavior; do not create duplicate tasks, rewards or messages. |  |  |  | Not reviewed
Operations | O04 | Late or missing event | Define how older updates are handled and how stale records are reconciled. A timestamp rule alone does not prove completeness. |  |  |  | Not reviewed
Operations | O05 | Destination outage | Name retry, alert, investigation and recovery owners. Memberply delivery retries do not implement destination processing retries. |  |  |  | Not reviewed
Operations | O06 | History and initial load | Define safe cutoff/reconciliation between the starting population and live events; do not assume full historical export. |  |  |  | Not reviewed
Operations | O07 | Handover | Record monitoring, credential rotation responsibility, change process and ongoing support agreement. |  |  |  | Not reviewed

## Acceptance tests
Section | ID | Decision / test | Guidance | Your response / actual result | Named owner | Evidence / reference | Status
Acceptance tests | T01 | Activation | A supported activation updates the correct store/customer and expected destination status and tier. |  |  |  | Not reviewed
Acceptance tests | T02 | Tier change | A supported tier change updates the intended record without restarting unrelated onboarding. |  |  |  | Not reviewed
Acceptance tests | T03 | Cancellation | Verify immediate cancellation clears or updates mapped active fields. Assess scheduled-cancellation requirements separately. |  |  |  | Not reviewed
Acceptance tests | T04 | Replay | Deliver the same event twice; confirm no duplicate task, message or reward and record the observed result. |  |  |  | Not reviewed
Acceptance tests | T05 | Late event | Process a newer state before an older event; confirm the agreed policy prevents a stale overwrite. |  |  |  | Not reviewed
Acceptance tests | T06 | Outage and recovery | Make the destination unavailable in a test environment; prove alerting, recovery and the eventual record update. |  |  |  | Not reviewed
Acceptance tests | T07 | Initial reconciliation | Compare agreed starting records and later changes with the destination; investigate missing or mismatched records. |  |  |  | Not reviewed
Acceptance tests | T08 | Store isolation and consent | Confirm different stores cannot update each other; confirm marketing preferences remain unchanged. |  |  |  | Not reviewed
Acceptance tests | T09 | Launch decision | Record unresolved failures, accepted limitations, decision owner, date and next review. No automatic readiness score. |  |  |  | Not reviewed

## Worked example
Section | ID | Decision / test | Guidance | Your response / actual result | Named owner | Evidence / reference | Status
Worked example | E01 | Outcome | Illustrative custom project, not a shipped connector: show active membership status and tier in an internal CRM. | Illustrative only |  |  | Not applicable
Worked example | E02 | Direction | Memberply to receiver to CRM. No CRM writes back to Memberply; no balances, billing or marketing subscription changes. | Illustrative only |  |  | Not applicable
Worked example | E03 | Inputs | Supported member.activated, member.tier_changed and member.cancelled events. Confirm payload and trigger coverage in current docs. | Illustrative only |  |  | Not applicable
Worked example | E04 | Identity | Use payload shop plus data.member.shopify_customer_id to resolve the CRM record within that store. | Illustrative only |  |  | Not applicable
Worked example | E05 | Mapping | Map data.member.status and data.membership.tier_name to agreed CRM display fields. Confirm real event payloads; do not treat the test payload as exhaustive. | Illustrative only |  |  | Not applicable
Worked example | E06 | Receiver responsibilities | Verify signature, persist or queue safely, deduplicate payload id, apply the agreed late-event policy, then update the destination. | Illustrative only |  |  | Not applicable
Worked example | E07 | History | Initial population and scheduled-cancellation dates remain feasibility questions until a supported source and reconciliation plan are agreed. | Illustrative only |  |  | Not applicable
Worked example | E08 | Acceptance | Activation reaches the right CRM record; a replay has no duplicate effect; outage recovery and stale-event handling pass recorded tests. | Illustrative only |  |  | Not applicable