## Read first
Purpose | Migration planning and evidence record only. This workbook does not import members, transfer rewards, change billing or undo actions.
How to use | Complete project scope, track each batch, reconcile comparable populations, plan billing/cutover and record a human launch decision.
Comparison rules | Use the same snapshot, store, tier/status scope and unit or currency in each row. Repeat rows per tier/currency. Do not sum overlapping cohorts or different units.
Difference formula | Destination minus source, only when both values are numbers. Blank means not entered, not zero. Zero difference alone does not establish matching members, valid access or correct billing.
Missing and zero | Enter a real numeric zero only when verified. Numbers stored as text leave the difference blank; confirm numeric entry before reviewing.
CSV alternative | CSV contains the blank reconciliation ledger only. Calculate differences manually. Scope, batch, billing, cutover, decision and worked-example sheets are Excel-only.
Safe sharing | Use evidence references and test identifiers. Keep customer-level exports, payment details and credentials in approved restricted systems.
Recovery | Pause expansion and investigate discrepancies. Deleting imported members does not automatically reverse rewards, payments or communications.
Guide | https://www.memberply.com/guides/shopify-loyalty-program-migration#migration-worksheet
Actual import template | https://help.memberply.com/import-members

## Project scope
Decision / stage | Guidance | Your plan / outcome | Owner | Due / review date | Evidence / status
Store and systems | Record source, destination store, account setup, tiers and migration owner.
Snapshot and cutoff | Record dated source snapshot, timezone and who captures joins, cancellations, redemptions and refunds after it.
Identity and eligibility | Approve record matching, tier mapping, active/inactive definitions and access dates; use stable identifiers.
Pilot | Select representative cases, including inactive, existing, recurring and exception records; agree expected outcomes.
Separate workstreams | Member import, points, store credit, gift cards and recurring payments each need an agreed treatment.
Data references | Link to access-controlled evidence. Do not paste customer exports, payment details or credentials into this shared plan.

## Reconciliation
Check ID | Batch / snapshot | Dataset / scope | Unit or currency | Source expected | Destination observed | Difference (destination - source) | Explanation / exception | Named owner | Evidence reference | Review status
R01 |  | Member records in agreed scope | records | [6 empty] | Not reviewed
R02 |  | Active memberships in agreed scope | memberships | [6 empty] | Not reviewed
R03 |  | Inactive memberships in agreed scope | memberships | [6 empty] | Not reviewed
R04 |  | Memberships in one mapped tier | memberships | [6 empty] | Not reviewed
R05 |  | Points remaining in agreed scope | points | [6 empty] | Not reviewed
R06 |  | Store credit remaining in one currency | specify currency | [6 empty] | Not reviewed
R07 |  | Gift card value in one currency | specify currency | [6 empty] | Not reviewed
R08 |  | Recurring payments confirmed for agreed cohort | subscriptions | [6 empty] | Not reviewed
R09 |  | Records changed after source snapshot | records | [6 empty] | Not reviewed
R10 |  | Additional reconciliation check | specify unit | [6 empty] | Not reviewed

## Batch outcomes
Decision / stage | Guidance | Your plan / outcome | Owner | Due / review date | Evidence / status
Batch identity | Record file/snapshot reference and tier/status scope. This worksheet is not the Memberply upload template.
Submitted rows | Record submitted count separately from unique members and membership assignments.
Created / updated / unchanged | Record each reported count and verify destination records rather than assuming all submitted rows succeeded.
Rejected / partial | List reported counts and restricted evidence references; partial rows may already have applied changes.
Retry decision | Identify only unresolved rows to retry after checking actual destination state. Preserve successful results.
Batch acceptance | Compare expected identities, eligibility and tier/status counts with destination evidence; name reviewer and date.

## Billing plan
Decision / stage | Guidance | Your plan / outcome | Owner | Due / review date | Evidence / status
Old final charge | Record the agreed old-system billing schedule and owner; import does not stop old billing.
New setup | Confirm supported new checkout/payment path and first-charge timing. Import does not establish a subscription.
Member deadlines | Review imported-member payment deadlines, reminder behavior and any access extensions before invitations.
Proof of new billing | Use restricted references to observed payment/subscription evidence. An invitation or active status is not proof.
Old billing retirement | Agree who confirms new billing and retires the old arrangement without duplicate or unintended charges.
Exceptions | Record unpaid, failed, delayed and disputed cases with an owner, communication and next review.

## Cutover plan
Decision / stage | Guidance | Your plan / outcome | Owner | Due / review date | Evidence / status
Before pilot | Approve source backup, tier/benefit configuration, access dates, initial balance treatment and test scope.
After pilot | Reconcile identities, eligibility, rewards and payment behavior; resolve unexplained differences.
Final changes | Capture and reconcile changes since the first snapshot; agree any freeze window explicitly.
Controlled batches | Process and inspect each batch; pause expansion for rejected/partial cases or unexpected effects.
Member journey | Test sign-in, active/inactive access, eligible benefits and connected tools on the intended account experience.
Communications | Approve audience, wording and timing separately for free and paid members; verify payment dates before sending.
Monitoring | Name who watches payments, balances, access and support requests after the switch.
Stop and recovery | Pause further imports/invitations when access, charges or balances are wrong. Agree a case-specific recovery plan; deletion is not an automatic reversal.
Source retirement | Retain required evidence and confirm remaining billing and balance obligations before retiring source workflows.

## Launch decision
Decision / stage | Guidance | Your plan / outcome | Owner | Due / review date | Evidence / status
Unresolved differences | List every unexplained count, balance, eligibility or billing difference and accountable owner.
Accepted limitations | Record explicit decisions, rationale and evidence for limitations; do not silently treat them as passed.
Go / no-go / limited pilot | Human decision only, with scope, approver, date and evidence. No formula certifies readiness.
Recovery authority | Name the person allowed to stop expansion and approve corrective actions; preserve member entitlements and payment evidence.
Next review | Record monitoring period, next review date and how outstanding cases will be closed.

## Worked example
Decision / stage | Guidance | Your plan / outcome | Owner | Due / review date | Evidence / status
Illustrative only | Same-store migration of 120 single-tier member records. Not a customer result; no actual imports or payments performed.
Batch outcome | 120 submitted: 114 created + 4 updated + 0 unchanged + 2 rejected + 0 partial = 120 outcomes. Only 118 intended records verified in the destination.
Reconciliation | Source 120, destination 118, difference -2. Do not mark complete. Investigate the rejected rows and reconcile identities before retrying only unresolved records.
Eligibility | Expected 100 active and 20 inactive; destination has 98 active and 20 inactive. The missing two active records still need review; counts alone do not prove correct access.
Existing credit | Source and destination each show USD 3,000 already held by Shopify in the same store. Zero difference is not a reason to issue another USD 3,000. Verify member-level ownership and pending activity.
Billing | Keep the billing workstream open until required new subscriptions and the old-billing retirement plan are verified. An imported active status does not prove payment setup.
Decision | Pause expansion, resolve the two exceptions, review balances/access/billing and record the accountable human decision.